## Risk Register
Risk ID | Category | Risk Statement | Likelihood (1-10) | Impact (1-10) | Risk Score | Key KRI | Green Threshold | Yellow Threshold | Red Threshold | Existing Controls | Additional Controls | Risk Response | Risk Owner | Residual Risk
1 | Strategic | AI Strategy Performance Risk | 6 | 8 | 48 | Warehouse productivity improvement rate | >15% | 10-15% | <10% | Project governance | Quarterly KPI review | Mitigate | Strategy Team | Medium
2 | Strategic | Workforce & Reputation Risk | 4 | 7 | 28 | Customer sentiment score | >80 | 60-80 | <60 | PR monitoring | Stakeholder engagement | Mitigate | HR & Communications | Medium
3 | Strategic | Competitive Technology Risk | 8 | 8 | 64 | Market share change (%) | Stable/Growth | 0 to -2% | <-2% | Competitive analysis | Innovation roadmap | Mitigate | Strategy Team | High
4 | Strategic | Third-Party Technology Dependency Risk | 7 | 5 | 35 | Vendor availability (%) | >99.5% | 98-99.5% | <98% | SLAs | Vendor diversification | Transfer | Vendor Mgmt | Medium
5 | Operational | Warehouse Automation Failure Risk | 7 | 9 | 63 | Downtime hours/month | <2 | 2-5 | >5 | Preventive maintenance | Redundant systems | Mitigate | Warehouse Ops | High
6 | Operational | Order Fulfillment Performance Risk | 5 | 7 | 35 | Order accuracy rate (%) | >99% | 97-99% | <97% | Quality checks | AI validation rules | Mitigate | Fulfillment Team | Medium
7 | Operational | Supply Chain Disruption Risk | 7 | 8 | 56 | Supplier on-time delivery (%) | >95% | 90-95% | <90% | Multi-sourcing | Supplier contingency plans | Mitigate | Supply Chain | Medium
8 | People | Workforce Adoption & Capability Risk | 6 | 6 | 36 | Training completion rate (%) | >95% | 85-95% | <85% | Training programs | Change management office | Mitigate | HR | Medium
9 | Technology | AI Decision Accuracy Risk | 8 | 8 | 64 | Forecast accuracy (%) | >95% | 90-95% | <90% | Model testing | ML monitoring & retraining | Mitigate | AI Team | High
10 | Technology | System Integration & Infrastructure Risk | 7 | 8 | 56 | System uptime (%) | >99.9% | 99-99.9% | <99% | Monitoring tools | Disaster recovery plan | Mitigate | IT Team | Medium
11 | Cybersecurity | Cybersecurity Breach Risk | 8 | 9 | 72 | Security incidents/month | 0-1 | 2-3 | >3 | MFA, SOC monitoring | Penetration testing | Mitigate | Security Team | High
12 | Financial | Automation Investment Performance Risk | 6 | 7 | 42 | Budget variance (%) | <5% | 5-10% | >10% | Budget tracking | Stage-gate approval | Accept/Mitigate | Finance | Medium
13 | Compliance | AI Governance & Compliance Risk | 5 | 8 | 40 | Compliance violations | 0 | 1-2 | >2 | Compliance audits | AI ethics review board | Avoid/Mitigate | Compliance Office | Medium

## Risk Control Matrix
Risk ID | Risk | Control Type | Key Control | Control Frequency | Control Owner
5 | Warehouse Automation Failure | Preventive | Robot maintenance | Weekly | Warehouse Ops
9 | AI Decision Accuracy | Detective | Model performance monitoring | Daily | AI Team
11 | Cybersecurity Breach | Preventive | MFA & access control | Continuous | Security Team
7 | Supply Chain Disruption | Preventive | Supplier diversification | Quarterly | Supply Chain
13 | Compliance Risk | Detective | Compliance audit | Quarterly | Compliance